## Sheet1
AI Nutritionist - Health academy website
Date | Hours | Task | Work Done
2025-09-13 | 1 | Meeting with Olga | We had a meeting and discuss about the projects
2025-09-20 | 2 | Tested chatbot | we received the files and got admin for wordpress, I run health academy website, tried to connect existing chatbot, but it seems not working well, I will look for another way
2025-09-24 | 0.5 | Created new repo in github | https://github.com/narkmn/HealthAcademyNen08
2025-10-03 | 3 | Wordpress analysis | Tried to run localhost in wordpress, Wordpress file was too big to download and run it.
2025-10-04 | 2 | Learning | Wordpress plugins and how to connect NextJS
2025-10-09 | 2 | Wordpress analysis | Used "All in One WP migration" plugin, still not very good success.
2025-10-16 | 3 | Wordpress migration | Tried Vivid backup and others, still have not worked, so emailed to Olga to ask hosting account.
2025-10-19 | 2 | Wordpress migration | Download healthacademy.ca files through the SSH connection, because FTP is not working.
2025-10-21 | 1 | Wordpress migration | Run the healthacademy in locally. However URLs are in website, tried to change it. But broke the database.
2025-10-23 | 2 | Wordpress migration | Prepared and configured healthacademy.ca in locally again. Also prepared midterm report
2025-10-25 | 4 | Wordpress migration | Prepared migration scripts, however database configuration is not working well, we only change it by manually, need to automate in bash terminal
2025-10-25 | 1 | Wordpress migration | Tested
2025-10-26 | 4 | Wordpress migration | No way to fix database configuration, so in the middle we have to import database name and change something, which is faster
2025-10-30 | 2 | Clouding | Purchased new webhosting in WHC, same as Healthacademy, and domain www.dataofattraction.com setting up
2025-11-03 | 6.5 | Clouding | Change the scripting code and migrated database and wordpress, still not fully automated but all the steps now clear
2025-11-05 | 2 | Testing | Testing on removing unnecessary plugins and pages, Removed 4 plugin and it worked okay