## Sheet1
AI Nutritionist - Health academy website
Date | Hours | Task | Work Done
2025-09-13 | 1 | Meeting with Olga | We had a meeting and discuss about the projects
2025-09-20 | 2 | Tested chatbot | we received the files and got admin for wordpress, I run health academy website, tried to connect existing chatbot, but it seems not working well, I will look for another way
2025-09-24 | 0.5 | Created new repo in github | https://github.com/narkmn/HealthAcademyNen08
2025-10-03 | 3 | Wordpress analysis | Tried to run localhost in wordpress, Wordpress file was too big to download and run it.
2025-10-04 | 2 | Learning | Wordpress plugins and how to connect NextJS
2025-10-09 | 2 | Wordpress analysis | Used "All in One WP migration" plugin, still not very good success.
2025-10-16 | 3 | Wordpress migration | Tried Vivid backup and others, still have not worked, so emailed to Olga to ask hosting account.
2025-10-19 | 2 | Wordpress migration | Download healthacademy.ca files through the SSH connection, because FTP is not working.
2025-10-21 | 1 | Wordpress migration | Run the healthacademy in locally. However URLs are in website, tried to change it. But broke the database.
2025-10-23 | 2 | Wordpress migration | Prepared and configured healthacademy.ca in locally again. Also prepared midterm report